## Sheet1
|  | Project Name: | Fundamental Project Specification: Inventory Management System (IMS)
|  | Project Description: | To create a functional application, using supporting tools, methodologies, and technologies, that encapsulates all fundamental modules covered during training.
|  | Project Owner: | Haaris Moghal
Risk ID | Date registered | Risk area | Risk description | Probability |  |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 10.05.21 | RSI | Staring at the screen for too long, causes eye strain and headaches. |  | x |  |  | x |  | Delay the progress of the project. | varies on the injury. | Take frequent breaks to prevent this.
2 | 10.05.21 | Connection issues with SQL | Not being able to connect to my database | x |  |  |  |  | x | connection issue to SQL would halt my progress on the project. | Time length depends on the issue being fixed. | Ask supervisors or Google Searching.
3 | 10.05.21 | Covid19 | The potential to contract the Corona Virus. Depending on impact it could lead me to be hospitalised or out for a few days. |  |  | x |  |  | x | Delay the progress of the project. | On going. | Follow government guidelines, stay in doors whenever it is possible.
4 | 18.05.21 | Lack of technical knowledge | New to testing java applications. Learning new testing techniques. | x |  |  |  | x |  | This will slow down the progress of my project completion. | On going. | Use the resources I have/been provided with.
5 | 20.05.21 | Damage hardware | Potential for my computer to break, SSD or HDD failure. | x |  |  |  |  | x | I would be unable to complete my project unless I fix the computer should the problem arise. | 2-3 days. | Maintain the computer storage and only keeping the necessary files. Aswell as the surronding of my pc setup, no food or drinks.
6 | 2021-05-27 | Time / Schedule management | Wasting time and not meeting personal deadliines (Kanban board) |  | x |  |  | x |  | Could potentially lead me to not being able to complete my project in time or at all. | On going. | Manage my time efficiently using application tools such as Jira.
7
8
9
10